## Sheet1
Description | Hours | Cost
Joing 14 sheets of ply wood into 7 sheets of 120cm*480 cm | 8 | 2800
glass single side of 4 sheets of plywood | 5 | 4000
glass double side of 4 sheets of plywood | 5 | 8000
Cut foam block(including lasercutting templates) | 4 | 1000
Cut plywood | 16 | 100
Glue hull together | 8 | 200
Glue strip of fiberglass over seams on inside of hull | 8 | 1000
Glue foam blocks in place | 3 | 200
Filler on outside of hulls | 8 | 1000
Sanding of outside of hulls | 8 | 500
Glassing of outside of hulls | 16 | 5000
Fairing of hulls | 16 | 1000
Painting of hulls | 10 | 2000
Cut and drill aluminium profiles | 10 | 2000
Welding of aluminium frame | 4 | 500
Install glass walls | 12 | 3000
Installl wood walls | 5 | 1000
Make ceiling | 6 | 4000
Install ceiling(cabling and welding) | 5 | 300
Make floor | 8 | 500
Install floor | 3 | 100
Install engines(cables, fuel hoses etc) | 10 | 40000
Install cleates , lifting eyes etc | 5 | 3000
Install hatches | 16 | 2500
Install bridge to hull | 4 | 300
Make trampoline | 6 | 600
Install trampoline | 2 | 400
Make deck | 10 | 2000
Install Deck | 4 | 400
Make railings/ stanchions | 6 | 800
Install railings | 4 | 100
Prefab electrics | 20 | 4000
Install electrics | 2 | 200
Make heating system(Brackets, adapters etc) | 6 | 500
Install diesel heater | 4 | 3000
Total(h/NOK) | 267 | 80100
Total(weeks/USD | 6.675 | 10012.5